# Search Buddy - PDF Training Guide Q&A
Implementation & Estimation

Two implementation approaches | One-person delivery estimate | Includes testing, production validation and buffer

Use case: users ask natural-language questions about application modules and the agent must answer using the relevant PDF training guides available on the Help page. The agent may also continue to support existing non-document module queries through current Search Buddy paths.

# 1. Executive Summary

| Approach | When to use | Build effort | Testing + Prod + Buffer | Total estimate |
| --- | --- | --- | --- | --- |
| Approach 1 - Reuse existing search/vector platform | Existing vector index/search service, security model and deployment pattern can be reused. | 15 working days | 13 working days | 28 working days (~5.5-6 weeks) |
| Approach 2 - Build a dedicated PDF RAG layer | Existing search/index cannot safely support the new training-document use case or a separate lifecycle/index is required. | 32 working days | 20 working days | 52 working days (~10-11 weeks; plan 10-12 weeks) |

Planning note: These are planning estimates for one primary engineer working sequentially. They assume timely SME access, stable environments and no major platform procurement. Business/SME approval waiting time may extend calendar duration but is not counted as active engineering effort.

# 2. Use Case and Target Behavior

Training guides are PDF documents, generally one guide per application module, stored and surfaced from the Help page.

A user may ask a general help question without explicitly naming the PDF or module.

The agent should identify whether the query belongs to a training-guide/document path or an existing Search Buddy/module path.

For training-guide questions, the system should retrieve the most relevant document chunks, preserve module/document metadata, and generate a grounded answer with source/page reference where supported.

New or updated training guides should become searchable through a repeatable ingestion process rather than ad-hoc manual indexing.

The existing Search Buddy testing model already covers query understanding, routing, retrieval, RAG synthesis, session state, ingestion/CDC, security and performance. The PDF feature therefore extends the existing search path rather than requiring a separate QA model.

# 3. Architecture Options

## 3.1 Approach 1 - Reuse Existing Search / Vector Infrastructure

Use the current document/search platform if it already supports chunk storage, embeddings/vector retrieval, metadata filtering, access controls and agent/tool integration. The new feature becomes an additional document corpus or module-specific index/namespace.

| PDF | Parse | Chunk + Metadata | Embed | Existing Vector/Search Index | Agent Retrieval | Grounded Answer |
| --- | --- | --- | --- | --- | --- | --- |

Primary implementation work:

Confirm the existing parser, chunking, embedding, index and security model can support training PDFs.

Define document metadata such as module, document ID, title, version, page/section and access scope.

Add or configure the PDF ingestion flow and index the training guides.

Add agent/router logic so training-guide questions use document retrieval while other questions continue to use existing module/search tools.

Add prompt/citation behavior, trace instrumentation, Golden test cases and regression gates.

## 3.2 Approach 2 - Build a Dedicated PDF RAG Layer

Build a separate ingestion and retrieval layer when the current search platform cannot be reused, when training documents need an independent lifecycle/security boundary, or when a dedicated vector index and retrieval configuration is required.

| Help-page PDF Store | Ingestion Job | Parser | Chunking | Embedding Service | New Vector Index | Retriever/Reranker | Agent + LLM |
| --- | --- | --- | --- | --- | --- | --- | --- |

Additional build work compared with Approach 1:

Design the document/index schema, metadata contract, versioning and lifecycle rules.

Build ingestion orchestration, parser/chunker, embedding generation, upsert/delete/re-index logic and failure handling.

Create/configure the vector index and, if required, keyword/hybrid retrieval and reranking.

Implement ACL/tenant filtering, document version precedence and observability from scratch for this path.

Integrate the new retriever as an agent tool and establish deployment, monitoring and production support.

# 4. Detailed Estimation - Approach 1

| Phase | Scope | Effort (days) | Type |
| --- | --- | --- | --- |
| Discovery & reuse assessment | Validate current search/vector architecture, PDF location, access model, supported metadata and reusable components. | 2 | Build |
| Document metadata & onboarding design | Define module/document/version/page/section metadata and indexing convention. | 2 | Build |
| PDF parsing & chunking integration | Configure parser/chunker; handle headings, tables and page metadata; connect to existing ingestion path. | 3 | Build |
| Embedding & index onboarding | Generate embeddings, load/update existing index/namespace, validate searchability. | 2 | Build |
| Agent routing / tool integration | Route training-document questions to document search and preserve existing module/tool behavior. | 3 | Build |
| Prompt, grounding & citation behavior | Build/adjust RAG prompt, no-answer behavior and source attribution. | 2 | Build |
| MLflow tracing / observability updates | Capture route, tool, retrieved chunks, scores, prompt/model version, latency, errors and token usage. | 1 | Build |
| Functional + integration testing | Parser, retrieval, routing, citations, no-result, update/delete and failure cases. | 3 | Testing |
| Golden dataset + offline AI evaluation | SME-approved representative questions; correctness, relevance, recall/precision, faithfulness and routing checks. | 2 | Testing |
| Regression / UAT | Run critical Goldens, known failures and business-critical help journeys. | 2 | Testing |
| Production deployment & smoke validation | Deploy, validate production-like retrieval, traces, security and initial monitoring. | 2 | Prod |
| Contingency / buffer | Environment issues, parser variation, retrieval tuning and defect retest. | 4 | Buffer |

Approach 1 total: 28 working days (~5.5-6 weeks for one person).

# 5. Detailed Estimation - Approach 2

| Phase | Scope | Effort (days) | Type |
| --- | --- | --- | --- |
| Discovery & target architecture | Confirm source location, lifecycle, security, search behavior, non-functional targets and integration boundaries. | 4 | Build |
| Schema / metadata / index design | Design document metadata, index schema, version strategy, IDs, filters and source precedence. | 4 | Build |
| Ingestion orchestration | Build repeatable load/update/delete pipeline with status, retry, idempotency and failure handling. | 4 | Build |
| PDF parser & chunking layer | Extract sections/pages/tables, chunk semantically and retain page/module/version metadata. | 4 | Build |
| Embedding pipeline | Embedding model integration, batching, limits, retry and re-embedding logic. | 3 | Build |
| Vector index / search layer | Provision/configure index, mappings, filters, hybrid/semantic retrieval and basic tuning. | 4 | Build |
| Retriever / reranker & relevance tuning | Top-K, keyword/vector balance, reranking and deduplication. | 4 | Build |
| Agent routing / tool integration | Add document-search tool and intent/routing logic; combine with existing module tools where needed. | 3 | Build |
| Grounding / prompt / citation behavior | RAG synthesis, source/page citations, no-answer/partial-answer behavior. | 2 | Build |
| Security & access filtering | ACL/tenant/module restrictions, sensitive-data handling and prompt-injection controls for document retrieval. | 2 | Build |
| MLflow tracing / observability | Trace ingestion/search/generation path; latency, errors, retries, tokens, model/index versions. | 2 | Build |
| Functional & component testing | Parser, chunking, embeddings, index, filters, retrieval and agent tool tests. | 4 | Testing |
| Integration / SIT | End-to-end PDF ingestion -> retrieval -> answer; update/delete, failure and recovery scenarios. | 3 | Testing |
| Golden dataset & AI evaluation | Build SME-approved Goldens and validate retrieval + response quality KPIs. | 2 | Testing |
| Regression / UAT | Critical scenario suite, existing-search regression and business validation. | 1 | Testing |
| Production deployment & validation | Deployment, smoke tests, initial quality/latency/security checks and monitoring. | 3 | Prod |
| Contingency / buffer | Provisioning, integration defects, PDF variability, tuning, retest and production readiness. | 7 | Buffer |

Approach 2 total: 52 working days (~10-11 weeks for one person). For planning, use a 10-12 week calendar range.

# 6. Effort Breakdown by Delivery Type

| Approach | Build / Configuration | Testing & UAT | Production Validation | Buffer | Total |
| --- | --- | --- | --- | --- | --- |
| 1 - Reuse existing platform | 15 days | 7 days | 2 days | 4 days | 28 days |
| 2 - Dedicated PDF RAG layer | 32 days | 10 days | 3 days | 7 days | 52 days |

# 7. Testing Scope Included in the Estimate

Document ingestion: valid/corrupt PDFs, duplicate documents, metadata completeness, update/delete and index visibility.

Chunking quality: section boundaries, multi-page tables, page/header retention and retrievability of answer-bearing content.

Retrieval quality: Precision@K, Recall@K / required-evidence coverage, Hit Rate, ranking/reranking and filtering.

Agent behavior: intent detection, correct document-search tool selection, fallback/no-answer behavior and existing-path regression.

RAG response quality: factual correctness, answer relevancy, faithfulness/groundedness, completeness and citation accuracy.

Security: ACL/tenant restrictions, sensitive-data masking and prompt-injection/adversarial document scenarios.

Non-functional: baseline latency, peak concurrency where environment permits, errors/retries, token usage/cost and observability.

Release regression: critical Golden cases plus representative high/medium cases after prompt/model/embedding/index/parser changes.

The existing strategy calls for component testing, offline AI evaluation, integration/SIT, UAT/business validation, regression/CI and production monitoring; those stages are included in the estimates above.

# 8. Assumptions and Dependencies

One primary engineer is assigned full-time; SME/Product/QA reviewers are available when needed.

PDF guides are approximately 8-10 pages on average and are mostly machine-readable; heavy scanned/OCR content may add effort.

Existing agent/LLM integration and authentication are already available.

Approach 1 assumes the current vector/search service supports a new corpus/namespace and required metadata/ACL filtering without major platform changes.

Approach 2 assumes cloud/network/security approvals do not introduce long procurement lead times.

The estimate includes implementation, testing, defect retest, production smoke validation and contingency; it does not include authoring the business training documents themselves.

Performance/load testing depth depends on access to a production-like environment and agreed QPS/concurrency targets.

# 9. Decision Guide

| Question | If YES | If NO |
| --- | --- | --- |
| Can the existing vector/search index store training-guide chunks with module/version/page metadata and required security filters? | Prefer Approach 1 | Move toward Approach 2 |
| Can the current ingestion path parse/chunk/embed new PDFs automatically on add/update/delete? | Approach 1 remains viable | Build missing pipeline components; likely Approach 2 |
| Can the agent already call the existing search layer as a tool and distinguish document-help intent from other module intents? | Small routing/configuration change | Additional agent/tool integration required |
| Do training guides need an independent lifecycle, access boundary, index tuning, or operational ownership? | Approach 2 may be safer | Approach 1 is usually simpler |

# 10. Recommended Next Step

Run a short 2-day technical discovery first. Validate whether the existing vector/search platform can support the PDF corpus, metadata, ACL filters, update/delete lifecycle, agent tool call and tracing requirements. If the answer is yes, proceed with Approach 1 and plan approximately 6 weeks. If one or more foundational capabilities are missing or require architectural changes, use Approach 2 and plan 10-12 weeks.